## Sheet0
STATE LOAD DESPATCH CENTRE Madhya Pradesh Power Transmission Company Limited, Jabalpur
From Date: | 2024-03-29
Control Area : | ALL | Circle : | ALL
S.NO. | APPLICATION DATE | REQ_ID | REQ TYPE | ELEMENT | SUBSTATION | CATEGORY TYPE | REASON FOR SHUT DOWN | PROPOSED START DATE & TIME | PROPOSED STOP DATE & TIME | Availing Officer Name & Mob. No. |  | REMARK
1 | 2024-03-21 10:19 | MR2403/0569 |  | 220KV_BUSCOUPLER along with Bus Tie | 220KV_AMARKANTAK | NON-OCCM-WR | New 220kv PMU panel Installation wo | 29-03-2024 09:00:00 | 29-03-2024 13:00:00 | Prashant Sharma | 8989986610 | element not clear
2 | 2024-03-28 15:31 | MR2403/0720 |  | 220KV_220kv Amarkantak-Sidhi ckt | 220KV_AMARKANTAK | NON-OCCM-MP | for disc replacement & other line work | 29-03-2024 10:00:00 | 29-03-2024 18:00:00 | JIDENDRA KUMAR TIWARI | 9425805298 | ok
3 | 2024-03-28 16:26 | MR2403/0722 |  | 132KV_MACT BHOPAL-AMRAWAT KHURD_Ckt | 132KV_AMRAWAT KHURD | NON-OCCM-MP | Flashover disc replacement work | 29-03-2024 10:00:00 | 29-03-2024 18:00:00 | Ankit Mehroliya | 9425804506 | sub ld
4 | 2024-03-28 15:43 | MR2403/0721 |  | 132KV_132KV Anuppur-H.J.I CKT | 220KV_ANUPPUR | NON-OCCM-MP | for disc replacement 220KV Amk-Sidhi ckt crossing | 29-03-2024 10:00:00 | 29-03-2024 18:00:00 | Jitendra kumar tiwari | 9425805298 | HJI consent required
5 | 2024-03-28 15:02 | MR2403/0718 |  | 220KV_220 KV Omkareshwar-Nimrani Tap Barwaha line | 220KV_BARWAHA | NON-OCCM-MP | Line maintance work | 29-03-2024 08:00:00 | 29-03-2024 18:00:00 | Naresh Pandre | 9425806905 | ok, through sub ld
6 | 2024-01-23 17:07 | MR2401/0392 | Daily | 220KV_BETUL CHHINDWARA | 220KV_BETUL | NON-OCCM-MP | for OPGW stringing work | 27-01-2024 07:00:00 | 25-05-2024 19:00:00 | SHIV KUMAR | 9425806917 | ok, line to be in service
7 | 2024-03-26 17:26 | MR2403/0676 | Continuous | 400KV_315 MVA TRANSFORMER NO. 2 | 400KV_BHOPAL4 | NON-OCCM-MP | For replacement the same by New 500MVA X-Mer | 27-03-2024 09:00:00 | 31-07-2024 18:00:00 | Akram Khan | 9425804695 | Differed from site
8 | 2024-03-28 11:21 | MR2403/0705 |  | 132KV_132 KV Bina - Mungaoli line | 220KV_BINA | NON-OCCM-MP | Auto to non auto mode for hot line work | 29-03-2024 10:00:00 | 29-03-2024 17:00:00 | Sanjay singh thakur | 9425806936 | ok, line to be in service
9 | 2024-03-28 12:03 | MR2403/0710 | Daily | 220KV_220 KV Bina- Sagar Ckt -2 | 400KV_BINA4 | NON-OCCM-MP | Auto to Non auto for OPGW work by M/s ZTT | 29-03-2024 07:00:00 | 30-04-2024 19:00:00 | Sanjay Singh Thakur | 9425806936 | ok, line to be in service
10 | 2024-03-28 11:59 | MR2403/0709 | Daily | 220KV_220 KV Bina - Sagar Ckt -1 | 400KV_BINA4 | NON-OCCM-MP | Auto to non auto for OPGW work by M/s ZTT | 29-03-2024 07:00:00 | 30-04-2024 19:00:00 | Sanjay Singh Thakur | 9425806936 | ok, line to be in service
11 | 2024-02-13 10:02 | MR2402/0194 | Daily | 220KV_220KV BINA DATIYA LINE | 400KV_BINA4 | NON-OCCM-MP | Live Line Hot Line Non Auto permit | 13-02-2024 07:00:00 | 05-05-2024 19:00:00 | SATISH KUMAR BHAGAT | 7049297785 | ok, line to be in service
12 | 2024-02-29 11:50 | MR2402/0546 | Daily | 220KV_220 KV Bina - Datia Ckt | 400KV_BINA4 | NON-OCCM-MP | Auto to non auto mode for OPGW work By ZTT | 01-03-2024 07:00:00 | 15-05-2024 19:00:00 | Sanjay singh thakur | 9425806936 | ok, line to be in service
13 | 2024-02-29 11:45 | MR2402/0544 | Daily | 220KV_220 KV Bina- Pichhore Ckt | 400KV_BINA4 | NON-OCCM-MP | Auto to non auto mode For OPGW work by ZTT | 01-03-2024 07:00:00 | 15-05-2024 19:00:00 | Sanjay singh thakur | 9425806936 | ok, line to be in service
14 | 2024-02-13 09:57 | MR2402/0193 | Daily | 220KV_220KV BINA PICHHORE | 400KV_BINA4 | NON-OCCM-MP | Live Line OPGW Installation work by ZTT | 13-02-2024 07:00:00 | 15-05-2024 19:00:00 | SATISH KUMAR BHAGAT AE TLM PICHHORE | 9425806916 | ok, line to be in service
15 | 2024-03-28 11:40 | MR2403/0706 |  | 220KV_220 kV Satna- Chhatarpur (MPPTCL) line | 220KV_CHATARPUR | NON-OCCM-MP | Damage Tension Hardware Replacement | 29-03-2024 09:00:00 | 29-03-2024 18:00:00 | Manoj Kumar Tiwari | 9425804993 | real time
16 | 2024-03-27 14:37 | MR2403/0694 | Daily | 132KV_MSP-220 KV DEWAS LINE | 132KV_DEWAS(MSP) | NON-OCCM-MP | FOR OPGW LAYING WORK | 27-03-2024 14:30:00 | 29-03-2024 19:00:00 | KAMAL SOLANKI | 9425805262 | sub ld
17 | 2024-03-27 14:34 | MR2403/0693 | Daily | 132KV_MSP-BNP LINE | 132KV_DEWAS(MSP) | NON-OCCM-MP | FOR OPGW LAYING WORK | 27-03-2024 14:30:00 | 29-03-2024 19:00:00 | KAMAL SOLANKI | 9425805262 | sub ld
18 | 2024-02-16 15:58 | MR2402/0269 | Daily | 220KV_220 kV Gorabazar-Amarkantak | 220KV_GORABAZAR | NON-OCCM-MP | installation of OPGW and recovery of Earth Wire. | 17-02-2024 07:00:00 | 30-04-2024 19:00:00 | Jitendra Tiwari | 9425805298 | ok, line to be in service
19 | 2024-03-15 10:16 | MR2403/0353 | Continuous | 400KV_Generating Unit No. 8 | 400KV_INDIRASAGAR | NON-OCCM-WR | Annual maintenance | 16-03-2024 06:00:00 | 31-03-2024 18:00:00 | Sh. Sanjay Patel | 9575074321 | as per system availability
20 | 2024-02-16 16:00 | MR2402/0270 | Daily | 220KV_220 kV Jabalpur Amarkantak (old circuit-II) | 220KV_JABALPUR | NON-OCCM-MP | installation of OPGW and recovery of Earth Wire. | 17-02-2024 07:00:00 | 30-04-2024 19:00:00 | Jitendra TIwari | 9425805298 | ok, line to be in service
21 | 2024-02-18 16:48 | MR2402/0289 | Daily | 400KV_400 kv Birsinghpur katni 1 | 400KV_KATNI4 | NON-OCCM-MP | For OPG stringing work | 24-02-2024 08:00:00 | 15-05-2024 18:00:00 | Pankaj Yadav | 9406713326 | ok, line to be in service
|  |  |  | 400KV_400 kv Birsinghpur katni 2 | 400KV_KATNI4 | NON-OCCM-MP | For OPG stringing work | 24-02-2024 08:00:00 | 15-05-2024 18:00:00 | Pankaj Yadav | 9406713326 | ok, line to be in service
22 | 2024-03-28 14:29 | MR2403/0716 |  | 132KV_132 kv Katni-Kaymor line CRT-2 | 400KV_KATNI4 | NON-OCCM-MP | line maintenance work. | 29-03-2024 10:00:00 | 29-03-2024 17:00:00 | pankaj yadav | 9406713326 | ok
23 | 2024-03-28 14:16 | MR2403/0714 |  | 220KV_220KV NIPANIYA BHANPURA LINE | 220KV_NIPANIYA | NON-OCCM-MP | Pre monsoon maint and testing work | 29-03-2024 13:00:00 | 29-03-2024 18:00:00 | Rambabu Nagar | 9425802879 | after normalisation of 400kv system at Mandsaur
24 | 2024-03-15 19:20 | MR2403/0385 | Continuous | 220KV_Bus A along with Bus Coupler | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual maintenance of unit 8 | 16-03-2024 10:00:00 | 30-03-2024 18:00:00 | Sh. Pankaj Sharma | 7898703187 | Continuous
25 | 2024-03-26 20:00 | MR2403/0678 | Continuous | 220KV_Generator UNIT 1 | 220KV_OMKARESHWAR | NON-OCCM-MP | Annual Maintenence of Unit 1 | 27-03-2024 11:00:00 | 10-04-2024 18:00:00 | PANKAJ SHARMA | 9425993027 | as per system availability
26 | 2024-01-23 18:40 | MR2401/0394 | Daily | 220KV_CHHINDWARA PANDHURNA | 220KV_PANDHURNA | NON-OCCM-MP | for OPGW stringing work | 27-01-2024 07:00:00 | 25-05-2024 19:00:00 | SHIV KUMAR | 9425806917 | ok, line to be in service
27 | 2024-03-27 12:37 | MR2403/0686 | Continuous | 132KV_63 MVA X-mer no -2 | 132KV_PIPARIYA1 | NON-OCCM-WR | For foundation making work 33 KV I/C-2 VCB & CT | 28-03-2024 09:00:00 | 01-04-2024 18:00:00 | B K Jhariya | 9525806831 | sub ld
28 | 2024-02-28 10:42 | MR2402/0500 | Daily | 132KV_132 KV Satna-Rampur Bahghelan line | 132KV_RAMPUR BAGHELAN | NON-OCCM-MP | OPGW wire stringing on line | 29-02-2024 08:00:00 | 31-03-2024 18:00:00 | Mirza M. Baig | 9425805067 | ok, line to be in service
29 | 2024-03-26 13:49 | MR2403/0663 | Continuous | 220KV_220 KV RATLAM-DALODA Load transfer | 220KV_RATLAM | NON-OCCM-MP | feeder bay from Old control room to New Control | 27-03-2024 12:00:00 | 29-03-2024 18:00:00 | NIKHIL DUNGE | 9425801487 | Continuous
30 | 2024-03-28 15:07 | MR2403/0719 |  | 132KV_40 MVA 1st Xmer | 132KV_REWA1 | NON-OCCM-MP | OLTC Oil replacement & pre monsoon maintenence | 29-03-2024 08:00:00 | 29-03-2024 18:00:00 | Mukesh Kumar | 9425805280 | O&M consent required
31 | 2024-03-02 12:31 | MR2403/0038 | Daily | 220KV_220 kv Satna-Rewa | 220KV_SATNA | NON-OCCM-MP | OPGW Stringing | 03-03-2024 08:00:00 | 31-03-2024 18:00:00 | AE TLM Satna | 9425805067 | ok, line to be in service
32 | 2024-03-02 12:40 | MR2403/0040 | Daily | 220KV_220 Satna-Birsinghpur line | 220KV_SATNA | NON-OCCM-MP | OPGW Stringing | 03-03-2024 08:00:00 | 31-03-2024 18:00:00 | Mirza M. Baig | 9425805067 | ok, line to be in service
33 | 2024-03-28 11:46 | MR2403/0707 |  | 132KV_132 KV SOHAGPUR-SEMRIHARCHAND LINE | 132KV_SEMRI HARCHAN | NON-OCCM-MP | new vd provide & JC tightening | 29-03-2024 10:00:00 | 29-03-2024 18:00:00 | Ashutosh Rai | 9425806902 | sub ld
34 | 2024-02-19 14:49 | MR2402/0307 | Daily | 220KV_220 KV Tikamgarh â¿¿ Damoh (MPPTCL) Line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Stringing work | 21-02-2024 07:00:00 | 30-04-2024 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
35 | 2024-02-19 14:53 | MR2402/0308 | Daily | 220KV_220 KV Tikamgarh â¿¿ Damoh (PGCIL) Line | 220KV_TIKAMGARH | NON-OCCM-MP | OPGW Stringing work | 21-02-2024 07:00:00 | 30-04-2024 19:00:00 | Manoj Kumar Tiwari | 9425804993 | ok, line to be in service
36 | 2024-03-28 14:46 | MR2403/0717 |  | 220KV_220KV INTERCONNECTOR IV | 400KV_UJJAIN4 | OCCM-MP | CT TANDELT MEASURMENT PRE MANSOON MAITENANCE WORK | 29-03-2024 10:00:00 | 29-03-2024 17:00:00 | S. Chavrasia | 9425804677 | ok, through sub ld
37 |  | 194866 |  | 220KV-MORENA-MEHGAON-1 | WR | WR | FOR LINE MAINTENANCE WORK |  |  |  |  | real time
38 |  | 194721 |  | 400KV/220KV KHANDWA-ICT-1 | WR | WR | LBB and Bus bar, simultaneous outage of 400KV BUS-2 is required for bus bar testing work.Dia to be kept open at both sides |  |  |  |  | ok
39 |  | 194868 |  | 400KV-CHHEGAON-KHANDWA-1 | WR | WR | LBB and Bus bar, simultaneous outage of 400KV BUS-2 is required for bus bar testing work.Line Amp,A/R off of 400KV-KHANDWA-KHARGONE-1 is required.Dia to be kept open both ends. |  |  |  |  | ok
40 |  | 191435 |  | 220KV-DAMOH-TIKAMGAD-1 | WR | WR | A/R off required for OPGW installation work |  |  |  |  | ok